## Sheet1
Feature | Phase | Description | Component | Subsystem | Must | Duration | Owner | Must Efforts
View current "Project" "Balance" | 1 | The project balance is visible to every user within the project, during the entire lifetime of it | Frontend | Balance | yes | 4 | FO | 4
Compare balance | 1 | The "Balance" adds all expenses of every individual in a project and compares them | Frontend | Balance | yes | 4 | FO | 4
Attached balance to task | 1 | Assign a balance to a task and attahced a receipt for it | Frontend | Balance | yes | 5 | FO | 5
Add a balance | 1 | A user can create a balance object holding effective costs, predicted costs, date and currency | Frontend | Balance | yes | 3 | FO | 3
Attache an image to a balance | 1 | A user can attach an image or photo taken to a balance | Frontend | Balance | yes | 4 | FO | 4
Develop Balance Module | 2 | Develop Balance subsystem and ist testcases (including UI) | Frontend | Balance | yes | 5 | FO | 5
Test balance module | 3 | Complete function test including fixing | Frontend | Balance | yes | 3 | FO | 3
Document Balance subsystem | 4 | Document the balance subsystem, including class diagram, Message Diagram and use cases | Frontend | Balance | yes | 5 | FO | 5
Send group Message | 1 | Users can send group messages to inidividuals which were selected from the global directory. The message has a sent, processed, received and read indicator that is displayed to the user, next to the message sent | Frontend | Chat | yes | 4 | FO | 4
Send private Message | 1 | A user can send messages of unlimitted length to one single individual, which he selects from the global directory | Frontend | Chat | yes | 2 | FO | 2
Open advanced "Project" "Chat" | 1 | Project members can initiate individual chats among them | Frontend | Chat | no | 4 | FO | 0
Send emoticon | 1 | A user can send emoticons in char messages | Frontend | Chat | no | 4 | FO | 0
Attached images to a chat | 1 | A user can attach images or pictures taken to a chat message, which will be displayed | Frontend | Chat | no | 4 | FO | 0
Open "Project" "Chat" | 1 | Every user can use a chat with all individuals from a project (default is group chat) | Frontend | Chat | yes | 2 | FO | 2
Send project chat messages | 1 | A user can send messages to everyone in a project | Frontend | Chat | yes | 4 | FO | 4
Receive Message | 1 | A user receives all messages from the individuals in a project | Frontend | Chat | yes | 2 | FO | 2
Forward messages | 1 | A user can forward messages into any other chat | Frontend | Chat | yes | 3 | FO | 3
Develop Chat Module | 2 | Develop chat subsystem and ist testcases (including UI) | Frontend | Chat | yes | 5 | FO | 5
Test Chat module | 3 | Complete function test including fixing | Frontend | Chat | yes | 3 | FO | 3
Document Chat subsystem | 4 | Document the balance subsystem, including class diagram, Message Diagram and use cases | Frontend | Chat | yes | 5 | FO | 5
Design Webservice to interact with Backend | 1 | The frontend communicates using a designed webservice to push and pull data | Backend | Communication | yes | 8 | CBS | 8
Design backend interface | 1 | Design the interface on how the frontend communicates with the backend | Interface | Communication | yes | 7 | CBS | 7
Develop Webservice | 2 | Develop the backen webservice and its testcases | Backend | Communication | yes | 10 | CBS | 10
Implement Webservice client | 2 | The frontend implementation of consuming the webservice an providing the modules with data | Frontend | Communication | yes | 9 | CBS | 9
Testing Webservice | 3 | Complete function test including fixing | Backend | Communication | yes | 6 | CBS | 6
Document Webservice | 4 | Document the Communication subsystem, including class diagram, Message Diagram and use cases | Documentation | Communication | yes | 6 | CBS | 6
Design Trace Messaging component | 1 | The system can log trace messages, which containt text, date time, severity and trace level for analysis purposes. The output will be a text file |  | Logging | yes | 6 | FO | 6
Develop Trace Messaging component | 2 | Develop Logging subsystem and ist testcases including interface |  | Logging | yes | 6 | FO | 6
Test logging component | 3 | Complete function test including fixing |  | Logging |  |  |  | 0
Document Trace component | 4 | Document the logging subsystem, including class diagram, Message Diagram and use cases |  | Logging | yes | 6 | FO | 6
Design "Project" model | 1 | Design the database model to store and retrive a project balance | Backend | Persistance Layer | yes | 6 | CBS | 6
Design "Balance" model | 1 | Design the database model to store and retrive balances | Backend | Persistance Layer | no | 6 | CBS | 0
Design "Message" model | 1 | Design the database model to store and retrive a chat message | Backend | Persistance Layer | yes | 6 | CBS | 6
Design "Poll" model | 1 | Design the database model to store and retrive polls including the votes | Backend | Persistance Layer | yes | 6 | CBS | 6
Design "Project" model | 1 | Design the database model to store and retrive a project | Backend | Persistance Layer | yes | 6 | CBS | 6
Design "Task" model | 1 | Design the database model to store and retrive a task | Backend | Persistance Layer | yes | 6 | CBS | 6
Design Global Directory | 1 | Design the global directory data structure | Backend | Persistance Layer | yes | 6 | CBS | 6
Develop Global Directory | 2 | Develop Global directory and its testcases (including UI) | Frontend | Persistance Layer | yes | 6 | CBS | 6
Testing directory | 3 | Complete function test including fixing | Backend | Persistance Layer | yes | 4 | CBS | 4
Document data model | 4 | Document data model and data dictionary | Documentation | Persistance Layer | yes | 8 | CBS | 8
Document directory subsystem | 4 | Document the Directory subsystem, including class diagram, Message Diagram and use cases | Documentation | Persistance Layer | yes | 4 | CBS | 4
Add poll Options | 1 | The owner of the poll can allow users to add their inidividual option, which is then available to all other users | Frontend | Poll | no | 3 | CBS | 0
Create a Poll | 1 | A user can create polls to vote between options. The options are defined when creating a poll. | Frontend | Poll | no | 6 | CBS | 0
Send Poll closed stats | 1 | Once every invited person has voted or the poll expired (datetime set when creating the poll => optional) the results are sent to either all users or the owner only, based on the settings made during opening of the poll | Frontend | Poll | no | 3 | CBS | 0
Set Poll expiry date time | 1 | The user can set an expiry for the poll at any time, as long as the poll is active. He will be notified when it expires, including the details | Frontend | Poll | no | 4 | CBS | 0
Vote on polls | 1 | The user creating the poll can select a list of users from the directory which are eligeable to vote for one of the specified options | Frontend | Poll | no | 3 | CBS | 0
Develop Poll Subsystem | 2 | Develop Poll Subsystem and its testcases (including UI) | Frontend | Poll | yes | 7 | CBS | 7
Testing Polls | 3 | Complete function test including fixing | Frontend | Poll | yes | 6 | CBS | 6
Document Poll subsystem | 4 | Document the poll subsystem, including class diagram, Message Diagram and use cases | Documentation | Poll | yes | 6 | CBS | 6
Create Advanced "Project" | 1 | Additionally a user can add Balance to a project | Frontend | Project | no | 1 | FO | 0
Get project balance notification | 1 | Users are being notified of effective costs involved with this project once it is closed | Frontend | Project | no | 4 | FO | 0
Create "Project" | 1 | A user can create a project which contains "Task", "Poll", "Chat" | Frontend | Project | yes | 3 | FO | 3
Invite user to "Project" | 1 | A user can invite individuals which were selected from the global directory. | Frontend | Project | yes | 2 | FO | 2
Kick user from "Project" | 1 | The owner of a project can kick individuals from it | Frontend | Project | yes | 1 | FO | 1
Close "Project" | 1 | The owner of a project can close it when finished | Frontend | Project | yes | 1 | FO | 1
Develop Project Module | 2 | Develop project subsystem and ist testcases (including UI) | Frontend | Project | yes | 5 | FO | 5
Test Project module | 3 | Complete function test including fixing | Frontend | Project | yes | 3 | FO | 3
Document Project subsystem | 4 | Document the balance subsystem, including class diagram, Message Diagram and use cases | Frontend | Project | yes | 5 | FO | 5
Design Reporting Model | 1 | Develop/design the reporting model, which allows you to report your projects, their effective balance, tasks, polls and chats involved along with some averages | Frontend | Reporting | no | 12 | CBS | 0
Develop Reporting model | 2 | Develop reporting subsystem and ist testcases (including UI) | Frontend | Reporting | no | 6 | CBS | 0
Testing Reporting | 3 | Complete function test including fixing | Frontend | Reporting | no | 6 | CBS | 0
Data and communication encryption | 1 | The data stored as well as realtime communication is being encrypted | Frontend | Security | no | 6 | CBS | 0
Assign task to user | 1 | The task owner can assign the task to another user within the project or chat group | Frontend | Task | yes | 3 | CBS | 3
Automated Task assignment | 1 | The system automatically assigns the task to a user for the given group, trying to build an equal load | Frontend | Task | no | 4 | CBS | 0
Create new Task | 1 | A user can create a task, containing a Title, detailed description, duration, due and start datetime. The task can furthermore contain a estimate spenditure allowance | Frontend | Task | yes | 6 | CBS | 6
Skillbased task assignment | 1 | Tasks can be assigned based on skills a user within the group has to have | Frontend | Task | no | 5 | CBS | 0
Task closure notification | 1 | A notification is sent to either the group or creator when the task is completed | Frontend | Task | no | 3 | CBS | 0
Develop Task Subsystem | 2 | Develop task subsystem and its testcases (including UI) | Frontend | Task | yes | 6 | CBS | 6
Testing Tasks | 3 | Complete function test including fixing | Frontend | Task | yes | 6 | CBS | 6
Document Task Subsystem | 4 | Document the task subsystem, including class diagram, Message Diagram and use cases | Documentation | Task | yes | 6 | CBS | 6
Design of frontend GUI | 1 | Design of the overall frontend look and feel including positioning of pannels | Frontend |  | yes | 18 | FO | 18
Floating panels | 1 | The user can rearrange panel as desired | Frontend |  | yes | 16 | FO | 16
285
369