## Sheet1
Task | Duration Estimated | Duration Effective Chris | Duration Effective Fabian | In Charge Planned | In Charge Effective
Project preparation
Documentation template | 16 | 0.5 |  | Christian Sax
Timesheets | 8 | 0.5 |  | Christian Sax
Proposal | 12 | 1.5 |  | Christian Sax
Project Preparation Completed |  | 2.5 | 0
Requirement Engineering
Project | 8 |  |  | Fabian Ochsner
Chat | 12 | 0 | 0 | Fabian Ochsner
Task | 16 | 4 |  | Christian Sax
Survey | 24 | 4.5 |  | Christian Sax
Accounting | 8 | 5 |  | Fabian Ochsner | Christian Sax, Fabian Ochsner
Reporting | 24 | 0
Security | 32 | 2.5 |  | Christian Sax
Backend
DB Model | 16 | 29.5 |  | Christian Sax
Interaction Layer | 12 | 10.5 |  | Christian Sax
Config Layer | 8 | 0 |  | Christian Sax
Backend Completed | 0
Webservice
Query Specification | 32 | 9.5 |  | Christian Sax
Update Specification | 40 | 11.5 |  | Christian Sax
Update Documentation | 48 | 3.5 |  | Christian Sax, Fabian Ochsner
UI Design | 32 | 21 |  | Fabian Ochsner | Christian Sax, Fabian Ochsner
Requirement Engineering Completed |  | 101.5 | 0
Imlementation
Project | 16 | 3.5 |  | Fabian Ochsner | Fabian Ochsner, Christian Sax
Chat | 24 | 0 |  | Fabian Ochsner
Task | 24 | 9.5 |  | Christian Sax
Survey | 32 | 17.5 |  | Christian Sax
Logging | 32 | 0 |  | Christian Sax
Accounting | 16 | 1 |  | Fabian Ochsner | Fabian Ochsner, Christian Sax
Reporting | 40 | 0
Security | 48 | 4.5 |  | Christian Sax
Webservice | 80 | 0 |  | Christian Sax
UI Implementation | 32 | 32.5 |  | Fabian Ochsner
Implementation Completed |  | 68.5 | 0
Testing
Specify TestCases | 40 | 7.5 |  | Fabian Ochsner, Christian Sax | Christian Sax, Fabian Ochsner
Project | 8 | 0 |  | Fabian Ochsner
Chat | 12 | 0 |  | Fabian Ochsner
Task | 12 | 8.5 |  | Christian Sax
Survey | 16 | 7.5 |  | Christian Sax
Logging | 8 | 0 |  | Christian Sax
Accounting | 8 | 4.5 |  | Fabian Ochsner
Reporting | 16 | 0
Security | 16 | 5
Webservice | 40 | 0
UI Implementation | 16 | 15.5 |  | Fabian Ochsner | Christian Sax, Fabian Ochsner
Testing Completed |  | 48.5 | 0
Follow up
Prepare official Documents | 16 | 9.5 |  | Christian Sax
Prepare Media | 16 | 2.5 |  | Christian Sax
Handover | 8 | 5.5 |  | Christian Sax
Grand Total | 924 | 459.5